## Plan1
Protocolo | Cliente | Projeto | Vistoria | Inversores | Marca
8000460278 | CLEITSON LECI BELTRAMINI | Aprovado | Aprovado | 1x12 | Deye |  |  | 1
8001120744 | IRINEU CARDOSO | Aprovado |  | 2x5 | Deye |  |  | 1
8001166358 | EVERTON DOS SANTOS SOARES | Aprovado | Aprovado | 1x5 | Deye |  |  | 1
8001740603 | OSMAR RAFAEL WATRAZ | Aprovado | Aprovado | 1x5 | SAJ |  |  | 1
8002286229 | MARCOS ANTONIO LEITE | Aprovado AR | Aprovado | 2x8 | Deye |  |  | 1
8003106414 | ADRIANO OSINSKI | Aprovado | Reprovado | 2x5 | Deye |  |  | 1
8001120201 | DOUGLAS SCHMITZ | Aprovado | Aprovado | 1x12 | Deye |  |  | 1
8001125046 | SIDENIR POLASTRI | Aprovado |  | 1x15 | Deye |  |  | 1
8001121676 | ELOI ANDRADE | Aprovado |  | 2x5 | Deye |  |  | 1
8001122262 | MILTON SPERANDIO | Aprovado AR |  | 1x60 | Deye |  |  | 1
8001123915 | MAURO SARDAGNA | [6 empty] | 1
8002834222 | MARCELO LUAN MATHIAS | Aprovado | Aprovado | 1x5 | Deye |  |  | 1
8003144354 | HILDA SADLOWSKI KALESKI | Aprovado | Aprovado | 1x12 | Deye |  |  | 1
8003385683 | CRISTIAN AIRSON LEMBECK | Aprovado | Aprovado | 2x5 | Deye |  |  | 1
8002630439 | SILVESTRE PUJAK | Aprovado | Aprovado | 2x5 | Deye |  |  | 1
8004891030 | JAIME BARABACH | Aprovado |  | 2x5 | Deye |  |  | 1
8001914823 | MAURELIO TOBIAS DE ANDRADE | Aprovado | Aprovado | 1x5 | Deye |  |  | 1
8005165031 | ASB COMERCIO DE MADEIRAS LTDA | Aprovado | Aprovado | 1x75 | Deye |  |  | 1
8002956025 | ANTONIO CICERO RIBEIRO | Aprovado |  | 2x5 | Deye |  |  | 1
8003021865 | LOURIVALDO SCHELL | Aprovado | Aprovado | 1x25 kW | Deye |  |  | 1
8003206911 | LUIZ ANDRE PANISSON | Reprovado |  | 2x5 | Deye |  |  | 1
8003038532 | VALDECIR ERHARDT | Reprovado |  | 1x50 kW | Growatt |  |  | 1
8003942921 | VALDECIR MACEDO MUNIZ | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8004389428 | JOSE ADAIR MARIOTI | Aprovado | Aprovado | 1x5H | Deye |  |  | 1
8002779576 | DAVID KELBERT | Aprovado | Aprovado | 1x12 | Deye |  |  | 1
8005549646 | DIONISIO KUHNEN | Aprovado |  | 1x5 | Deye |  |  | 1
8005549001 | MICHELLY VON BOEMEL | [6 empty] | 1
8005596545 | EVERALDO AURELIO DE SOUZA | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8005911870 | CELIO DA SILVEIRA | Aprovado | Aprovado | 1x15 kW | Deye |  |  | 1
8007118108 | AIRES GONCALVES | Aprovado | Aprovado | 1x5 kW | Deye |  |  | 1
8007347560 | JOEL SCHMITZ | Aprovado | Aprovado | 1x5 kW | Deye |  |  | 1
8007455793 | JOANIR VANDERLINDE | Aprovado | Aprovado | 4x8 kW | Deye |  |  | 1
8002610925 | SILVIO ZANELLA | Aprovado | Aprovado | 1x12 kW | Deye |  |  | 1
8007758821 | VALDECIR OSINSKI | Aprovado | Aprovado | 1x12 kW | Deye |  |  | 1
8008570319 | RODRIGO DA SILVA | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8008306549 | ODAIR WARMELING | [6 empty] | 1
8008308253 | JANETTE SCHULZZE ANDRE | [6 empty] | 1
8008311554 | ANDRE FERNANDES STEFFEN | [6 empty] | 1
8009494970 | JOHANES NITZ | Aprovado AR | Aprovado | 2x5 kW | Deye |  |  | 1
8008684938 | VITOR SCHLICKMANN | Aprovado | Aprovado | 1x5 kW | Deye |  |  | 1
8008906814 | BERNARDO EGER | Aprovado | Aprovado | 1x5 kW | Deye |  |  | 1
8005904131 | RUBENS SCHLICKMANN | Aprovado | Aprovado | 1x12 kW | Deye |  |  | 1
8009411035 | ANDRE FERNANDES STEFFEN | baixa tensao | [5 empty] | 1
8009409545 | OSNI MAULL | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8012366002 | CLEIDINEI VERMOLLEN | Aprovado | Aprovado | 1x25 kW | Deye |  |  | 1
8010639988 | LUIS HENRIQUE CECHELERO | Aprovado AR | Aprovado | 1x12 kW | Deye | 2025-12-18 |  | 1
8008614749 | JOSE EUNISIO FRANZ | Aprovado |  | 1x20 kW | Deye |  |  | 1
8008615489 | JOSE NOVAKOWSKI | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8008616263 | ANGELO NOVAKOWSKI | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8008616755 | LUZIA SADLOWSKI | Aprovado | Aprovado | 1x5 kW | Deye | 2025-12-20 |  | 1
8008571936 | SANDRO RIBEIRO | Aprovado AR | Aprovado | 2x5 kW | Deye |  |  | 1
8008857340 | ADRIANO KOBREN | Aprovado | Em Analise | 2x5 kW | SAJ |  |  | 1
8008840260 | LAURI CACKOVSKI | Aprovado | Aprovado | 1x12 kW | Deye |  |  | 1
8009779095 | RENATO LOFFI | Aprovado |  | 2x8 kW | Deye |  |  | 1
8009778712 | AMARILDO FRANCISCO | Aprovado | Aprovado | 2x8 kW | Deye |  |  | 1
8009987448 | LUCAS ORACZ | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8009992042 | JOCELIO RESSEL | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8009993612 | ORIVALDO DUMS | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8011025866 | RENATO POPOVICZ | outra UC | Em Analise | 2x5 kW | Deye |  |  | 1
8011030736 | LUIZ CARLOS CZORNEI | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8011032160 | SANDRA ALVES DA SILVA OSINSKI | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 1
8011285275 | ELOI ANDRADE | Aprovado | Aprovado | 2x5 kW | Deye |  |  | 61
8011287668 | ADRIANO OSINSKI | Aprovado | Aprovado | 2x5 kW | Deye
8011288193 | IRINEU CARDOSO | Aprovado | Aprovado | 1x5 kW | Deye
8011288891 | ANTONIO CICERO RIBEIRO | Aprovado | Aprovado | 2x5 kW | Deye
8011289163 | DIONISIO KUHNEN | Aprovado | Aprovado | 1x5 kW | Deye
8011289772 | JAIME BARABACH | Aprovado | Aprovado | 2x5 kW | Deye
8009777221 | JOSE MUCHENSKI | Aprovado | Aprovado | 2x5 kW | Deye
8010878850 | MARILDO BRUNO DEBARBA | Aprovado | Aprovado | 1x15 kW | Deye
8012514769 | JAIR BONA | Aprovado | Aprovado | 1x5 kW | Deye
8012353946 | JOSINEI DA CRUZ | Aprovado | Aprovado | 2x5 kW | Deye
8012670277 | JANETTE SCHULZZE ANDRE | Aprovado AR | Aprovado | 1x75 kW | Deye
8012965715 | SAMUEL JUBANSKI | Aprovado | Aprovado | 2x5 kW | Deye
8012367079 | ANCELMO DE BARROS | Aprovado AR | Aprovado | 1x12 kW | Deye
8015019741 | IVO FAVARIN JUNIOR | Aprovado | Aprovado | 2x5 kW | Deye
8012366796 | ILDO EISING | Aprovado | Aprovado | 1x5 kW | SAJ
8012366440 | VILSON MATTEUCCI | Aprovado | Aprovado | 2x5 kW | Deye
8012363724 | MARCOS JUSTEN | Aprovado AR | Aprovado | 1x20 kW | Deye
8012353663 | JAIMIR HOEPERS | Aprovado AR | Aprovado | 1x15 kW | Deye
8012353250 | SUYAN LOURENCO DA NAHAIA PAVANELLO | Aprovado | Aprovado | 1x5 kW | Deye
8012352964 | ENEDIR ODELLI SEVEGNANI | Aprovado | Aprovado | 1x5 Kw | Deye
8010202209 | SERGIO KALUZNY | Aprovado | Em Analise | 2x5 kW | SAJ | 2025-10-22
8010341106 | JOSIANE APARECIDA DIAS DA SILVA | Aprovado |  | 2x5 kW | Deye
8010505651 | JACILDO MATHIAS | Aprovado | Aprovado | 2x5 kW | Deye
8010877951 | DENISE ELLER BENSIE | Aprovado | Aprovado | 1x5 kW | Deye
8010877601 | ODAIR WARMELING | Cancelado |  | Ampliação | Fronius+Deye
8011662959 | CEZAR URBANEK | Aprovado | Aprovado | 2x5 kW | Deye | 2025-12-20
8012262298 | VILMAR AGOSTINHO | Aprovado | Aprovado | 2x5 kW | Deye
8012514246 | DENISE GAMBA PAZETTO | Aprovado | Aprovado | 1x12 kW | Deye | 2025-12-02
8012686107 | ODAIR WARMELING
8012731247 | ADEMIR RAITZ | Aprovado | Aprovado | 1x15 kW | Deye
8013140158 | ROGERS MANNERICH DE OLIVEIRA ME | Aprovado | Aprovado | 2x5 kW | Deye
8013375334 | ANTONIO OENNING | Aprovado | Aprovado | 1x15 kW | Deye
8014091410 | MARCOS HILDEBRANDT | Aprovado AR | Aprovado | 2x8 kW | Deye
8015020391 | RENATO POPOVICZ | Aprovado | Aprovado | 2x5 kW | Deye
8015021157 | SIDENIR POLASTRI | Aprovado | Aprovado | 1x15 kW | Deye
8014863309 | VALMOR HILLESHEIM | Aprovado | Aprovado | 2x5 kW | Deye | FAZER DEPOIS o Aumento 2x8
8015018304 | VOLNIR SILVA | Aprovado | Aprovado | 1x12 kW | Deye
8015961015 | EDEVALDO GROSSKLAUS | Em Analise |  | 1x12 kW | Deye
8012466170 | MAURICIO HILLESHEIM | Aprovado | Aprovado | 1x12 kW | Deye
8014046935 | MAICON MOACIR GESSER
8015154262 | ANDRE SCHIESTEL | Aprovado AR | Aprovado | 2x8 kW | Deye | 2025-12-20
8015600075 | ADRIANO KOBREN | Aprovado | Aprovado | 2x5 kW | SAJ
8016582962 | RONEI GOMES OLIVEIRA | Aprovado AR | Aprovado | 2x10 kW | Deye
8017458540 | CLEITON MOURA | Aprovado | Aprovado | 1x12 kW | Deye
8015613865 | MICHELLY VON BOEMEL | Em Analise |  | Ampliação | Goodwe + Deye
8014423404 | ROBERTO PANCHENIAK FILHO | Aprovado | Aprovado | 1x12 kW | Deye
8014961585 | MIGUEL PANCHENIAK | Aprovado | Aprovado | 2x5 kW | Deye
8015020820 | IRINEU CARDOSO | Aprovado | Aprovado | 1x5 W | Deye
8016162745 | ELIZITO BENCZ | Aprovado | Aprovado | 1x15 kW | Deye
8019037094 | OSMAR KLEGIN | Aprovado | Aprovado | 1x12 kW | Deye
8016500831 | MLC PRE MOLDADOS LTDA | Aprovado | Aprovado | 1x30 kW | SAJ | 2025-12-02
8001119066 | MN INSTALACOES LTDA | Aprovado AR | Aprovado | 1x30 kW | SAJ
8016864070 | ANTONIO MONTAGNA NETO | Aprovado | Aprovado | 1x5 kW | Deye
8018096638 | NILSON SCHRODER | Aprovado | Aprovado | 2x5 kW | SAJ
8016436111 | ANA CAROLINA PREIS | Aprovado AR | Aprovado | 2x5 kW | Deye | 2025-12-20
8016583233 | DOUGLAS HAMES | Aprovado | Aprovado | 2x5 kW | Deye
8016896416 | JAILSON JAIR BONA | Aprovado | Aprovado | 1x5 kW | Deye | 2025-12-21
8016898112 | JAYR PAVANELLO | Aprovado | Aprovado | 1x5 kW | Deye | 2025-12-21
8016899216 | CELSO HELLMANN | Aprovado | Aprovado | 1x40 kW | Deye | atualizar para 1x50 kW
8018148820 | JAIR BLASIUS | Aprovado | Aprovado | 1x20 kW | Deye
8018398359 | LUCIANE GREIM | Aprovado |  | 2x5 kW | Deye
8018389153 | SIGOLD SCHNEIDER | Aprovado | Aprovado | 1x5 kW | Deye
8018677254 | MAICON MOACIR GESSER | Aprovado |  | 2x5 kW | Deye
8018765840 | MARINO TENFEN | Aprovado | Aprovado | 1x15 kW | Deye
8018836631 | MARCIANO SCHNEIDER | Aprovado | Aprovado | 1x5 kW | Deye | 2025-12-21
8018837102 | EDIR ROEPKE | Aprovado | Aprovado | 1x12 kW | Deye
8019007956 | JOAO NIEPICUY | Aprovado | Aprovado | 2x5 kW | Deye
8019190509 | AMAURI DUARTE | Aprovado |  | 1x5 kW | Deye | SAJ
8019191020 | EBERSON VAHL | Aprovado | Aprovado | 1x5 kW | Deye
8019191380 | CLESIO JOSE HOEPERS | Aprovado | Aprovado | 2x5 kW | Deye
8019808035 | GILMAR RODRIGUES | Aprovado | Aprovado | 1x5 kW | Deye
8019808595 | LIRIO WARMELING | Aprovado | Aprovado | 1x5 kW | Deye
8019806503 | ONEIDE MARQUEZ | Aprovado | Aprovado | 1x12 kW | Deye
8019976117 | EDERSON GREIM | Não trouxe ART
8020345987 | EMERSON CORREA | Aprovado | Aprovado | 1x12 kW | Deye
8020659006 | RUBENS CREUTZBERG | Aprovado | Aprovado | 1x5 kW | Deye
8020782095 | ROBERTO MAUESKI | Aprovado | Aprovado | 1x25 kW | Deye
8017771197 | MARCELO CHIODINI | Aprovado | Aprovado | 1x5 kW | Deye
8020832583 | VALMIR FRANCISCO BILK | Aprovado |  | 1x15 kW | Deye
8020943430 | VEVERSON MENEGALLI | Aprovado | Aprovado | 1x5 kW | Deye | 1x8 KW Regularizar
8020943994 | HILARIO VETTER | Aprovado | Aprovado | 2x5 kW | Deye
8021009205 | EVALDINO JOSE SCHROEDER | Aprovado | Aprovado | 2x8 kW | Deye | 2026-03-02
8021064450 | GABRIELA MORASTONI | Aprovado | Aprovado | 2x5 kW | Deye
8021064759 | IVONE GARCIA CIPRIANI | Aprovado | Aprovado | 1x5 kW | Deye
8021065128 | SERGIO BELETTI | Aprovado | Aprovado | 2x5 kW | Deye
8021065418 | ANTONIO SENEM | Aprovado | Aprovado | 1x5 kW | Deye
8021065645 | DACENA MATERIAIS ELETRICOS LTDA. | Aprovado | Aprovado | 1x12 kW | Deye
8021816489 | ELCIO LUIZ ANDERLE | Aprovado | Aprovado | 1x12 kW | Deye
8021835996 | EDEVALDO GROSSKLAUS | Aprovado |  | 1x15 kW | Deye
8016637361 | ESTANISLAU WATRAZ | Aprovado AR | Aprovado | 1x12 kW | Deye
8021807657 | CELSO VERDI | Aprovado | Aprovado | 2x7,5 kW | Deye
8021827938 | FABIANO CARLOS MEGLIN | Aprovado | Aprovado | 1x3 kW | SAJ
8023271178 | ANTONIO ARLINDO PIANESSER | Cancelado
8023270223 | JOSE LUNELLI | Aprovado | Aprovado | 1x5 kW | Deye
8023342413 | EDMILSON ANTONIO BILK | Aprovado | Aprovado | 1x15 kW | Deye
8021656861 | JUAREZ DE SOUZA | Aprovado | Aprovado | 1x12 kW | Deye
8022456486 | DAIANA APARECIDA SANDNER | Aprovado | Aprovado | 1x15 kW | Deye
8022575198 | VIRGILIO MURCESKI | Cancelado |  |  |  | Mudar para 2x8 depois
8022892835 | NABOR FRANZEN | Aprovado | Aprovado | 2x5 kW | Deye
8025882807 | AMAURI DUARTE | Aprovado | Aprovado | 1x5 kW | SAJ
8024885731 | ALDAIR KEMPER | Aprovado | Aprovado | 1x5 kW | Deye
8025175572 | GUEROLT DENZER | Cancelado
8024374608 | ALFRED NILO DEBATIN | Aprovado | Aprovado | 2x5 kW | Deye
8024373971 | WALDEMIRO ELI | Aprovado | Aprovado | 1x12 kW | Deye
8026515918 | ANDRE REUTER | Aprovado | Aprovado | 1x20 kW | Deye
8026582964 | IVO GROSS | Aprovado | Aprovado | 2x5 kW | Deye
8026583002 | JOSE BRANGER | Aprovado | Aprovado | 1x5 kW | Deye
8026646815 | LUCIA LENZI | Aprovado AR | Aprovado | 1x25 kW | Deye
8026648142 | JAIR VICENTE | Aprovado | Aprovado | 1x5 kW | Deye
8026648728 | RAFAEL KNUPFER | Aprovado | Aprovado | 1x5 kW | Deye
8026327230 | SILVIO NAZARKIEWCZ | Cancelado |  | 2x5 kW | Deye | Depois Arrumar 2x8
8025730530 | ANAIR SALETE CORBANI KNIESS | Aprovado | Aprovado | 1x12 kW | Deye
8025731211 | ELONIR JOSE HELLMANN | Aprovado | Aprovado | 1x25 kW | Deye
8025177319 | AGNES ROPKE | Aprovado |  | 1x12 kW | Deye
8025177424 | DORIVAL PASCOAL LUNELLI | Aprovado | Aprovado | 2x5 kW | Deye
8027005690 | ODAIR WARMELING | Em Analise |  | 1x27 kW 1x20 kW 1x25 kW | FRONIUS DEYE DEYE
8018422112 | ROSANA HELLMANN ALVES | Aprovado AR | Aprovado | 2x8 kW | Growatt
8025175445 | SILVANA DA SILVA SCOTTINI | Aprovado | Aprovado | 1x5 kW | Deye
8029816434 | NIVALDO STAIDEL | Aprovado | Aprovado | 2x5 kW | Deye
8026928476 | AROLDO DE FREIN | Aprovado | Aprovado | 1x15 kW | Deye
8027371252 | ROGERIO SIMONI | Aprovado | Aprovado | 1x3 kW | SAJ
8031443585 | LORIVALDO STUPP
8027568407 | TERCILIO UDENIR SCOTTINI | Aprovado | Aprovado | 1x3 | SAJ
8027802120 | CARINA VALCANAIA | Aprovado | Aprovado | 1x5 kW | SAJ
8027863208 | GEDEONI ALBINO | Aprovado | Aprovado | 1x5 kW | SAJ
8027863835 | JOSEFA DA SILVA DOS SANTOS | Aprovado | Aprovado | 1x4 kW | Deye
8027960591 | CATIA CASTELANI | Aprovado | Aprovado | 1x5 kW | SAJ
8027961085 | ELISIO LOCH | Aprovado | Aprovado | 1x12 kW | Deye
8027961472 | SIRLENE MARIA CIRICO LEITE | Aprovado | Aprovado | 1x5 kW | SAJ
8028149941 | CLAUCIO SUCHARA | Aprovado | Aprovado | 1x5 kW | SOLIS
8028209337 | MURILO COELHO | Aprovado | Aprovado | 2x5 kW | Deye
8028209345 | WILMAR MARCELINO | Aprovado |  | 2x5 kW | SAJ
8035547485 | ADEMAR COELHO | Aprovado AR | Aprovado | 2x8 kW | Deye | 2025-05-12 | 2025-12-04
8028811925 | IVO PAUL | Aprovado | Aprovado | 1x5 kW | SAJ
8028811699 | ESTANISLAU DROZDA | Aprovado | Aprovado | 1x5 kW | SAJ
8028783914 | EDSON DE JESUS PEDROSO | Aprovado | Aprovado | 1x5 kW | Deye
8029357630 | DULCE MORATELLI TAMBOSI | Aprovado | Aprovado | 1x12 kW | Deye
8029356380 | JUARES LOKS | obra |  | 1x60 kW | Deye | 2025-04-28
8029850337 | LUCILVANIO VASELESKI | Aprovado | Aprovado | 2x5 kW | SAJ
8029850264 | MARCELI FELDMANN | Aprovado | Aprovado | 1x3 kW | Deye
8029850161 | MARCIEL MARCELINO | Aprovado | Aprovado | 1x5 kW | SAJ
8029850126 | IRCEBIDO GONCALVES | Aprovado | Aprovado | 1x5 kW | SAJ
8029815798 | JAIME WALATEK | Aprovado | Aprovado | 2x5 kW | Deye
8031439775 | CLARA REGINA RUCINSKI | Aprovado | Aprovado | 1x5 kW | SAJ
8030293959 | ALVARO TRAVAGLIA | Aprovado | Aprovado | 1x5 kW | SAJ
8031438014 | IVORLEI DA SILVA | Aprovado | Aprovado | 2x5 kW | Deye
8032681505 | GERALDO KUCZKA | Aprovado |  | 1x5 kW | SAJ
8032681984 | TIAGO NUNRBERG | Trocar Protocolo
8032681147 | ADRIANO AMARANTE | Aprovado | Aprovado | 2x5 | SAJ | Depois Arrumar 2x8
8032911022 | GABRIELA MORASTONI | Aprovado | Aprovado | 2x8 kW | Deye
8030891506 | MAURO CIPRIANI | Aprovado | Aprovado | 2x5 kW | SOLIS
8033135059 | ADEMIR ALVES VALENTE | Aprovado | Aprovado | 1x12 kW | Deye
8031261121 | SILVIO NAZARKIEWCZ | Aprovado | Aprovado | 2x5 kW | Deye
8026414573 | VIRGILIO MURCESKI | Aprovado | Aprovado | 2x5 kW | Deye | Depois Arrumar 2x8
8032499706 | ADEMIR MAYER | Aprovado | Aprovado | 1x4 kW | Deye
8032499042 | ARLINDO MAYER | Aprovado | Aprovado | 1x12 kW | Deye
8030284210 | ORLANDA PIRES | Aprovado | Aprovado | 1x5 kW | SOLIS | enc10
8030293896 | MAIKE DENZER | Aprovado | Aprovado | 1x5 kW | SAJ
8030287550 | OSNI SCHMIDT | Aprovado | Aprovado | 1x5 kW | SAJ
8035553223 | SALETE LEMOS DO NASCIMENTO | Aprovado | Aprovado | 1x5 kW | SAJ
8030287291 | JANETE APARECIDA PEREIRA | Aprovado | Aprovado | 1x5 kW | SAJ
8030287376 | NELSON STACHOLSKI | Aprovado | Aprovado | 1x5 kW | SAJ
8030279340 | PAULO CÉSAR TORQUATO | Aprovado |  | 1x5 kW | SAJ
8030293919 | CLAUDIO ADRIANO BECKER | Aprovado | Aprovado | 1x5 kW | SAJ
8030577872 | OSNI MUCHENSKI | cancelado
8030579391 | JOSE EDIMAR KUCHLLER | Aprovado | Aprovado | 1x5 kW | SOLIS | enc17
8030434077 | ANTONIO ARLINDO PIANESSER | Aprovado |  | 1x20 kW | Deye
8027005373 | VALDECIR ERHARDT | Aprovado AR | obra | 1x50 kW | Growatt
8033543196 | JOSE ITAMAR ANGELO | Aprovado | Aprovado | 2x8 kW | Deye | juare
8033542535 | PATRICIA MEURER ANGELO | Aprovado | Aprovado | 1x5 kW | SAJ
8033544852 | ROSEMERI DO PRADO | Aprovado AR | Aprovado | 2x3 kW | SAJ | 2025-06-10 | 2025-12-11
8033523938 | HILARIO BILESKI | Aprovado |  | 2x5 kW | SAJ
8033533228 | LUCIO TOMACHEVSKI | Aprovado | Aprovado | 2x5 kW | Deye | enc10
8033534762 | CELIO TOMACHEVSKI | Aprovado | Aprovado | 2x5 kW | Deye | enc10
8033536185 | MARCELO VAN BOEMMEL | Aprovado | Aprovado | 1x12 kW | Deye
8033537199 | VIVIANE BLASIUS | Aprovado |  | 1x7,5 kW | SAJ
8033541189 | JOSE AIRES DE BARROS | Aprovado | Aprovado | 1x5 kW | SAJ
8033544582 | JUSCELI DA SILVA SARDO | Aprovado | Em Analise | 1x5 kW | SAJ
8033385320 | JOEL CLASEN | REPROVADO |  | 1x75 kW | DEYE
8031260915 | MOACIR JOAO DE OLIVEIRA | alterar protocolo |  | 1x4 kW | Deye
8034101768 | MOACIR JOAO DE OLIVEIRA | Aprovado | Aprovado | 1x4 kW | Deye
8033108900 | MUNICIPIO DE PALMEIRA | Aprovado | Aprovado | 1x15 kW | SAJ
8033105851 | GUEROLT DENZER | obra |  | 2x6 kW | SAJ | 2025-05-03
8033102826 | LUIS GABARDO LEMOS | Aprovado | Aprovado | 1x5 kW | SAJ
8034403837 | MAISSON JOSE LOCKS | Aprovado | Aprovado | 1x3 kW | SAJ
8034348214 | FELIPE SARDO | Aprovado | Aprovado | 2x5 kW | SAJ
8033693967 | MADALENA CASTELANI | Aprovado | Aprovado | 1x5 kW | SAJ
8033700013 | IDALCINO SELINGER | Aprovado | Aprovado | 1x3 kW | SAJ
8033699799 | LIRIO NASS | Aprovado |  | 2x5 kW | SAJ
8033845743 | EDINELSON AFONSO CORREA | Aprovado | Aprovado | 2x5 kW | DEYE
8035765378 | MICHAEL VOGENIAK BILIK | cancelado
8032270345 | TEREZA FEY | Aprovado | Aprovado | 1x5 kW | SAJ
8032712171 | CLAUDIO VALMOR BECKER | Aprovado AR | Aprovado | 1x15 kW | DEYE
8032709881 | JESSICA LAIS DA SILVA FOSS | Aprovado | Aprovado | 1x5 kW | SAJ | 2025-04-16
8031486013 | IVAO NOVACK | Aprovado | Aprovado | 1x3 kW | SAJ | enc17
8033616136 | JUNIOR LUIZ BERTOTI | Aprovado | Aprovado | 1x5 kW | SAJ
8033889580 | ZENOVIA DERNYS | Aprovado | Aprovado | 1x5 kW | SAJ
8032712176 | CONSTRUTORA E INCORPORADORA FL LTDA | Aprovado | Aprovado | 1x5 kW | SAJ | 2025-04-16
8031488432 | JEAN CARLOS RIEG | Aprovado | Aprovado | 1x5 kW | SAJ
8033833366 | LEOMAR WATRAZ | Aprovado | Aprovado | 2x5 kW | SAJ
8029256244 | BRUNO FELCZAK | Aprovado AR | Aprovado | 2x8 kW | DEYE
8029230258 | INGO ROBERTO REIMER | Aprovado |  | 1x15 kW | DEYE
8029254536 | JEOVANE VANDERLINDE | Cancelado
8034766144 | JOAO MARCIO FERENS | Aprovado | Aprovado | 1x15 kW | DEYE
8028209340 | SIDNEI NANIA | Cancelado
8035635721 | ELISEU BOSSY | Aprovado | Aprovado | 2x5 kW | SOLIS
8031486765 | ALICE DAGOSTIN | Aprovado | Aprovado | 1x15 kW | DEYE | n
8031488028 | JOAO BATISTA MAZOTI | Aprovado |  | 1x15 kW | DEYE
8031488738 | VALCIR COSTA | Aprovado | Aprovado | 1x5 kW | SAJ
8031546421 | ERISOLETE HANCHUKA BECKER | Aprovado | Aprovado | 1x3 kW | SAJ
8031546980 | VILSON SAVIO FUSINATO | Aprovado |  | 1x5 kW | SAJ
8036001034 | DARIO PINZAGHER | Cancelado
8032274249 | NILTON KRAMBECK | Aprovado | Aprovado | 1x5 kW | SAJ
8032274892 | ALMIR DE SOUZA | Aprovado | Aprovado | 1x5 kW | SAJ
8032709760 | ELCIO HOEPERS | Aprovado |  | 2x5 kW | SAJ
8032709812 | ELTON PABLO DELL AGNOLLO | Aprovado |  | 2x5 kW | SAJ
8032712173 | JOSIMAR BUENO | Aprovado | Aprovado | 1x15 kW | DEYE
8032712204 | MARCOS AURELIO DOS SANTOS | Aprovado | Aprovado | 1x5 kW | SAJ
8033143432 | CLEBER REILI MASOTE | Aprovado | Aprovado | 1x5 kW | SAJ
8033143680 | GEOVANI DE OLIVEIRA | Aprovado | Aprovado | 1x5 kW | SAJ
8033143743 | LUIZ FRARE | Aprovado | Aprovado | 1x5 kW | SAJ
8033889790 | JOAO KUBICHEN | Aprovado | Aprovado | 1x5 kW | SAJ
8033889951 | AMARILDO BILIK | Aprovado |  | 1x5 kW | SAJ
8034071617 | CLEITON MENSOR | Aprovado | Aprovado | 2x5 kW | SAJ
8034764984 | LEONARDO BARA | Aprovado | Aprovado | 1x5 kW | SAJ
8034766439 | CARLITO ROBES | Aprovado | Aprovado | 1x5 kW | SAJ
8035075721 | MARLISE NARDI | Aprovado | Aprovado | 1x5 kW | SAJ
8035228986 | MARIA DE LURDES KEPP DE ESPINDOLA | Aprovado | Aprovado | 1x3 kW | SAJ
8035405298 | JEAN CARLOS BUZZI | Aprovado | Aprovado | 1x25 kW | SAJ
8035406361 | CLAUDENIR SENSI | Aprovado | Aprovado | 1x5 kW | SAJ
8035405661 | ELIVERTON SUAVE | Aprovado | Aprovado | 1x5 kW | SAJ
8035742944 | SAUL CAPISTRANI | Aprovado | Aprovado | 1x5 kW | SAJ
8036310112 | REINALDO KOPPES | Aprovado | Aprovado | 2x5 kW | SAJ
8036309394 | OSNI MUCHENSKI | Aprovado | Aprovado | 2x5 kW | SOLIS
8036310602 | TIAGO NUNRBERG | Aprovado | Aprovado | 1x5 kW | SAJ
8036003457 | MICHAEL VOGENIAK BILIK | Aprovado | Aprovado | 1x5 kW | SAJ
8036578241 | CLAUDENIR SENSI EPP | Aprovado | Aprovado | 1x5 kW | SAJ
8036579808 | MARCELO DA MAIA | Aprovado | Aprovado | 1x5 kW | SAJ
8036523931 | PAULO VIEIRA | Aprovado | Aprovado | 1x3 kW | DEYE
8037538806 | HELITON PAULO TIBES DA SILVA | Aprovado |  | 2x5 kW | SAJ
8037870910 | JANUARIO SCHMIDT | Aprovado | Aprovado | 1x12 kW | DEYE
8035996816 | IVO MENEGHELLI | Aprovado | Aprovado | 1x15 kW | DEYE
8036696716 | ALBERTO PREIS | Aprovado |  | 1x15 kW | DEYE
8037765839 | IRIA LUZIA STEFFEN | Aprovado | Aprovado | 2x5 kW | SAJ
8037765949 | NELSO ODORIZZI | Aprovado | Aprovado | 1x15 kW | SAJ
8037766949 | JOSE LUIECKMANN | Aprovado | Aprovado | 1x5 kW | SAJ | n
8037766966 | TEODOSIO BILESKI | Aprovado AR | Aprovado | 1x5 kW | SAJ | 2025-06-18
8038645141 | MAICON MOACIR GESSER | Aprovado AR | obra | 1x15 kW | SAJ | 2025-06-24
8039099880 | FLORENTINO ZANCANARO | Aprovado | Aprovado | 1x3 kW | SAJ | n
8039099885 | CIDNEI BLASIUS | Aprovado
8039099908 | VIVALDO KOPPES | Aprovado | Aprovado | 1x5 kW | SAJ
8039099945 | POSTO ALTO SANTA TEREZINHA | Aprovado AR | Aprovado | 1x30 kW | SAJ | 2025-06-18
8039099959 | GILBERTO TENFEN | Aprovado | Aprovado | 2x5 kW | SAJ
8038984384 | NELSO FRANCISCONI | Aprovado |  | 1x4 kW + 1x20 kW | DEYE
8038985181 | ADAIR ALVES | Aprovado | Aprovado | 1x5 kW | SAJ
8038755357 | DITER MICHEL | Aprovado | Aprovado | 1x5 kW | SAJ | n
8038760930 | VIVIANE BLASIUS | Aprovado | Aprovado | 7,5 kW | DEYE
8038761474 | JUSCELI DA SILVA SARDO | Aprovado | Aprovado | 1x5 kW | SAJ
8039328229 | ARLEI VENDRAMI | Aprovado | trocar inversor | 1x20 kW | DEYE
8039328504 | VANIO LUIZ MOSER | Aprovado AR | Aprovado | 1x15 kW | DEYE | 2025-06-21 | 2026-01-21
8037945785 | EDUARDO DEBATIN | Aprovado | Aprovado | 1x40 kW | DEYE
8039512114 | CELSO HELLMANN | Aprovado |  | 1x50 kW | DEYE
8039513227 | ALEXANDRE CHIKOSKI | Aprovado | Aprovado | 2x4 kW | DEYE
8037295993 | LUIZ CARLOS ESTEVAO | Em Analise |  | 1x25 kW | DEYE
8039944598 | ELCIO HOEPERS | Aprovado |  | 1x5 kW | DEYE
8039946515 | LIRIO NASS | Aprovado | Aprovado | 2x5 kW | WEG
8035655599 | GILMAR REINALDO GERALDI | Aprovado | Aprovado | 1x5 kW | DEYE
8040200327 | JAMES DE OLIVEIRA | Aprovado | Aprovado | 1x3 kW | SAJ
8040205168 | VILSON ALBRECHT | Aprovado | Aprovado | 1x5 W | SAJ
8035717461 | ANTENOR NIQUELLATTI | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-04-22
8040376050 | PAULO CÉSAR TORQUATO | Aprovado | Reprovado | 1x3 kW | SAJ
8040377587 | JAIR RIBEIRO | Aprovado |  | 1x5 kW | SAJ
8033897261 | NILO BERNARDO HILLESHEIM | Aprovado |  | 1x15 kW | DEYE
8041065859 | PERGENTINO MANARIN | Aprovado | Aprovado | 1x6 kW | SAJ
8041008768 | JOCENEI HELLMANN | Aprovado | Aprovado | 1x5 kW | SAJ
8041078845 | JANDIRA DE ANDRADE | Aprovado | Aprovado | 1x3 kW | SAJ
8041079052 | ROBERTO RIVELINO MATIAS | Aprovado | Aprovado | 1x5 kW | SAJ
8038756935 | CLEITON ALEXANDRE TOSE | Aprovado | Aprovado | 1x5 kW | SAJ | n
8038757166 | JADIEL OSVALDO ERN | Aprovado | Aprovado | 1x3 kW | SAJ
8038757572 | CLAUDINEI RODRIGUES | Aprovado | Aprovado | 1x5 kW | SAJ
8041846457 | ELENO CESAR WARMELING | Aprovado |  | 1x30 kW | SAJ
8042345194 | JARDEL BONETTI | Aprovado AR | Aprovado | 1x15 kW | SAJ | 2026-03-18
8042718869 | DEONISIA KORENIVSKI | Aprovado |  | 1x3 kW | SAJ
8042974940 | MARCIO DUNS
8012666873 | LAERCIO TOMELIN | Aprovado | Reprovado | 1x12 W | DEYE
8043050205 | ALCEU DUBIELA | Aprovado | Aprovado | 1x3 kW | SAJ
8043050885 | MADEIREIRA CCT LTDA ME | Aprovado | Aprovado | 1x5 kW | SAJ
8043693665 | MARCIO DUNS | Aprovado | Aprovado | 1x5 kW | SAJ
8043825439 | ISMAEL WILIAM DEBIAZZI | Aprovado |  | 1x5 kW | SAJ
8043812119 | VALCIR CACHOEIRA | Aprovado | Aprovado | 2x5 kW | SAJ
8043803236 | SIRLENE FORTUNA DOGNINI | Aprovado | Aprovado | 1x5 kW | SAJ
8043802994 | RENATO SCHEURICH | Aprovado | Aprovado | 1x25 kW | SAJ
8044281178 | LUIZ CARLOS ESTEVAO | Aprovado | Aprovado | 1x25 kW | DEYE
8044162743 | JOELDES DOERNER | Aprovado | Aprovado | 2x5 kW | SAJ
8044223746 | ADILSON IGLIKOWSKI | Aprovado | Aprovado | 2x5 kW | SAJ
8044144136 | VALDECIR ERHARDT | Aprovado | Aprovado | 1x30 kW | SAJ
8044162520 | OSMAR FAVARIN | Aprovado | Aprovado | 1x12 kW | DEYE
8044220515 | LUIZ ANDRE KALATAY | Aprovado |  | 2x5 kW | SAJ
8044220859 | VANDERLEI NIENKOTTER | Aprovado |  | 1x5 kW | SAJ
8044455252 | ALMIR CARLOS CIPRIANI | Aprovado | Aprovado | 1x5 kW | SAJ
8044478917 | LEONE BACK | Aprovado | Aprovado | 2x5 kW | SAJ
8044479496 | LEONARDO NESTOR BACKES | Aprovado |  | 2x5 kW | SAJ
8044974941 | FABRICA DE CONSERVAS BELETTI | obra |  | 1x50 kW | SAJ
8045314031 | JOSE PITSCH | Aprovado |  | 1x6 kW | SAJ
8044974622 | CELSO HELLMANN | Aprovado AR | Aprovado | 1x60 kW | DEYE | 2026-03-30
8044974150 | ELENO CESAR WARMELING | Aprovado | Aprovado | 1x25 kW | SAJ
8045449843 | JOSE ARNO NIENKOTTER | Aprovado | Aprovado | 1x5 W | SAJ | 2026-01-16
8045872180 | ALVARO LUIS MARCOS | Aprovado | Aprovado | 1x12 kW | DEYE
8045977571 | RENATO BECKER | obra |  | 2x8 kW | DEYE | 2025-08-26
8045726432 | ROLF DAHLKE | obra |  | 1x30 kW | SAJ | 2025-09-05
8045726017 | LUIZ PATEL | Aprovado | Aprovado | 1x12 kW | DEYE
8046436061 | TULIO MARIO MONDINI | Aprovado | Aprovado | 2x5 kW | SAJ
8046480094 | RENATO SCHALDACH | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-09
8046506751 | ADENIR CIPRIANI | Aprovado | Aprovado | 1x6 kW | SAJ | tiag
8046507469 | JOAO SILMAR MARTINS | Aprovado | Aprovado | 1x6 kW | SAJ
8046809428 | GABRIEL HELLMANN | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-01-22
8047058205 | SANDRO SOARES | Aprovado | Aprovado | 1x5 kW | SAJ
8047757724 | RALF STALOCH | Aprovado | Aprovado | 1x15 W | SAJ
8047843907 | MARCELO FERNANDES | Aprovado | Aprovado | 1x5 kW | SAJ
8047844231 | EMANOELE FERNANDES | obra |  | 1x5 kW | SAJ
8047904617 | AURORA CARTURANO | Aprovado | Aprovado | 1x3 kW | SAJ
8047709836 | AGNES ROPKE | Aprovado |  | 1x15 kW | SAJ
8047700799 | CLEYTON JOSE BARBETTA | Aprovado | Aprovado | 1x5 kW | SAJ
8047700402 | LUCIA SEMANN | Aprovado | Aprovado | 2x5 kW | SAJ
8048122287 | ROSELI KOPP DE OLIVEIRA BRANCO | Aprovado | Aprovado | 1x5 kW | SAJ
8045726238 | VILMAR WARMELING | Aprovado | Aprovado | 1x30 kW | SAJ | 2026-01-23
8048376758 | ARLEI VENDRAMI | Aprovado | Aprovado | 1x15 W | SAJ
8048377244 | OSMAR SCHMITZ | Aprovado | Em Analise | 1x15 kW | WEG
8048378017 | ADRI-MAR INDUSTRIA E COMERCIO DE MADEIRAS LTDA - ME | Aprovado |  | 1x30 kW | SAJ
8048404709 | AGOSTINHO SCHELL | Aprovado | Aprovado | 1x20 kW | WEG
8048477713 | SANDRO SCHLICKMANN | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-22
8048475657 | ALBERTO PREIS | Aprovado | Aprovado | 1x15 kW | SAJ
8048918329 | EDEVALDO GROSSKLAUS | Aprovado | Aprovado | 1x12 kW | DEYE
8048918959 | AIRSON MARTINS | Aprovado | Aprovado | 1x5 kW | SAJ
8048919825 | EVALDO PETROSKI | Aprovado | Aprovado | 1x3 kW | SAJ
8048707235 | MARCIO LANZNASTER | Aprovado | Aprovado | 1x15 kW | SAJ
8048681239 | DOUGLAS HILLESHEIM | Aprovado | Aprovado | 1x25 kW | SAJ
8048655431 | ADENICIO JOSE DE SOUZA | Aprovado | Aprovado | 1x5 kW | SAJ
8049268498 | NELI PEREIRA | Aprovado | Aprovado | 1x25 kW | SAJ
8049288637 | SALESIO HOEPERS | Aprovado | Aprovado | 1x20 kW | SAJ
8049288826 | JUSSARA VALENCIO ROHLING | Aprovado | Aprovado | 1x5 kW | SAJ
8049289184 | LAENIO WESSLER | Aprovado | Aprovado | 1x5 kW | SAJ | 2025-10-31 | 2026-01-16
8047279970 | DILMA EMA SCHLICKMANN | Aprovado | Aprovado | 1x5 kW | SAJ
8050646155 | JOAO BATISTA MAZOTI | Aprovado | Aprovado | 1x15 kW | SAJ
8050011389 | JOSE CARLOS NUSS | Aprovado AR | Aprovado | 1x15 kW | SAJ | 2026-03-27
8050305928 | ERMINIO VOLTOLINI | Aprovado |  | 1x5 W | SAJ
8050526612 | WIT FARMA FARMACIA | Aprovado | Aprovado | 2x8 kW | SAJ
8050527031 | DANILO BOING | Aprovado | Aprovado | 1x5 kW | SAJ
8051285753 | ISAILTON CHIQUELEIRO | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-03-31
8051441299 | VITORINO KLAUMANN | Aprovado | Aprovado | 1x15 W | SAJ
8050997847 | IRIS MONDINI | Aprovado | Aprovado | 1x5 kW | SAJ
8050997877 | MARCEL MENEGHELLI | Aprovado | Aprovado | 1x5 kW | SAJ
8050997904 | KEDMA MAHYARA DE OLIVEIRA | Aprovado | Aprovado | 1x5 kW | SAJ
8050998177 | JONAS DOS SANTOS | Aprovado | Aprovado | 1x3 kW | SAJ
8051033969 | JAIR RODRIGUES | Aprovado | Aprovado | 1x20 kW | SAJ | 2026-01-26
8051034378 | ISONE DA ROSA
8051840591 | TIAGO COELHO | Aprovado | Aprovado | 1x5 kW | SAJ
8051663676 | OSMAR INACIO | Aprovado | Aprovado | 1x5 kW | SAJ
8052077176 | ADELINO STEFFEN | Aprovado | Aprovado | 1x5 kW | SAJ
8052149936 | MIRIAN PAIM DE JESUS | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-03-23
8052148564 | LOURIVALD LAUE | Aprovado | Aprovado | 1x5 W | SAJ
8052114396 | CIDNEI BLASIUS | Aprovado | Aprovado | 1x15 kW | SAJ
8048476917 | GERALDO BELTRAME | Aprovado | Aprovado | 2x5 kW | SAJ
8052930447 | ANDERSON KORMANN | Aprovado |  | 1x15 kW | SAJ
8052576162 | PAULO SERGIO LUNELLI | Aprovado | Aprovado | 1x5 W | SAJ
8053305246 | OSMAR LATAUCZESKI | Aprovado | Aprovado | 2x5 kW | SAJ
8053437617 | SAVINO LUNELLI | Aprovado | Aprovado | 1x5 kW | SAJ
8054172185 | JOSE DA SILVA SOBRINHO | Aprovado | Aprovado | 1x5 kW | SAJ
8053437638 | ELTON WESTPHAL | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-20
8053437575 | ANTONIO CARLOS SESTREM | Aprovado | Aprovado | 1x3 kW | SAJ
8053706924 | JONAS ANGELO BONA | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-02-20
8054023518 | AMARILDO HASKEL | Aprovado | Aprovado | 1x5 kW | SAJ
8054175945 | INEZ BORGONHO FRONZA | Aprovado | Aprovado | 1x3 kW | SAJ
8054388660 | TEREZITA PINTO DE FAVERI | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-19
8054396581 | MARCELO HAVERROTH | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-14
8054412730 | GUSTAVO HENRIQUE DE AVIZ DA SILVA | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-03-31
8054644939 | GILBERTO KURTH | Aprovado |  | 1x15 W | SAJ
8054612536 | DARIO KRAMBECK | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-14
8055020061 | VANDERLEI TAMANINI | Aprovado | Aprovado | 2x7,5 kW | SAJ | 2026-02-20
8055481362 | MARLISE SOCREPPA WARMELING | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-01-12
8055327578 | OSMAR DA SILVA | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-27
8055369551 | JOAO SZOLOMICKI | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-01-20
8055407944 | ISRAELA TRAPP | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-16
8055529514 | IRMA ALEXANDRE | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-26
8056123966 | SOLANGE ANTUNES DUARTE FANTON | obra |  | 1x5 kW | SAJ | 2026-01-22
8056124191 | VALDEMAR ABREU | obra | Em Analise | 2x5 kW | SAJ | 2026-01-23
8056132000 | CHARLENE SCHMIDT TENFEN | Aprovado | Aprovado | 1x5 kW | SAJ
8056514788 | OSMAR SCHMITZ | Aprovado | Aprovado | 1x15 kW | WEG
8056511542 | OSMAR LUIZ | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-22
8056566599 | PEDRO DE SOUZA | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-02-03
8056566661 | CLARICE FLORIANI VERMOHLEN | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-03-10
8056566648 | EMIR PAHL | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-15
8056865858 | ADEMIR ZANELA | Aprovado |  | 1x5 kW | SAJ
8056866910 | FERNANDA SARTORI KEINER | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-09
8057098763 | EDERSON FELICIO ADRIANO | obra |  | 1x6 kW | SAJ
8057205906 | APARECIDA PINTO | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-15
8057324598 | JOAREZ ANGELO | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-22
8057342768 | CARLOS EDUARDO SESTREM | Aprovado |  | 1x15 kW | SAJ
8057342830 | SUELI CONZATTI | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-26
8054198725 | LUIZ MARCIANO | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-02-20
8054198883 | EDUARDO DA SILVA | Reprovado | Padrão Errado | 1x5 kW | SAJ
8057522744 | GUSTAVO HENRIQUE INACIO | Aprovado AR | Aprovado | 2x5 kW | SAJ | 2026-04-16
8057897454 | LEANDRO CANDIDO | Aprovado | Aprovado | 1x5 W | SAJ | 2026-02-25
8058031691 | NORTON GREGORY HENNING LISBOA BUENO | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-26
8058031281 | JULIANO SELINGER | Aprovado |  | 1x5 kW | SAJ
8058168125 | ADRI-MAR INDUSTRIA E COMERCIO DE MADEIRAS LTDA - ME | Aprovado | Aprovado | 1x30 kW | Growatt | 2026-01-16
8058165071 | ADEMIR ZANELA | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-16
IVAN FUSINATO CRIAR PROTOCOLO GRUPO A
8059208023 | ADILSON SCHUTZ | obra |  | 1x30 kW | SAJ | 2026-01-20 | Depois aumentar para 36
8060089360 | ANTONIO CARLOS SESTREM | Aprovado | Em Analise | 1x3 kW | SAJ
8059631200 | EDUARDO DA SILVA | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-16
8058331274 | LUIZ AUGUSTO PACKER BERTOLI | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-02-26
8062566101 | MARIA MARLENE PADILHA NEU | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-03-04
8062319548 | JAIR MATTEUCCI | Aprovado | Aprovado | 1x6 kW | SAJ
8062301542 | ELIZA BELTRAME BELLI | Aprovado | Aprovado | 1x5 kW | RENOVIGI | 2026-02-09
8059671534 | ARCANGELO EDUARDO CAVILIA | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-26
8059671562 | MARIA CLAUDINARA DE SOUZA | Aprovado |  | 2x5 kW | SAJ
8058359012 | LEONARDO DOS SANTOS | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-01-26
8058331881 | JOSE INACIO | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-22
8060089788 | JOSE LINO CONINCK |  |  | 1x75 kW
8063598278 | ADRIANA LOTERIO | Aprovado | Aprovado | 1x3 kW | SAJ
8059744378 | TARCISIO CIPRIANI | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-02-03
8057522080 | CRISTIAN AIRSON LEMBECK | Aprovado AR | Aprovado | 2x8 kW | DEYE | 2026-05-20
8063473184 | ANTONIO CARLOS SESTREM | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-01-27
8063634168 | CLAUDINEI JOSE POSSAMAI | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-02-09
8069662218 | BRUNA CRISTINA RODRIGUES MOSER | Aprovado | Aprovado | 1x5 kW | SOLIS
8063969174 | VALDEMAR ANTONIO DA SILVA | Aprovado | Aprovado | 2x7.5 kW | SAJ | 2026-03-10
8063968964 | SILVIO FABICHAKI | obra |  | 2x7.5 kW | SAJ | 2026-02-23
8063969073 | SALETE APARECIDA DALMARCO | Aprovado |  | 1x5 kW | SAJ
8063969350 | DIRCEU GREIM | Aprovado | Aprovado | 1x6 W | SAJ | enc 23/04
8063969677 | MARCELO GREIM | Aprovado | Aprovado | 2x5 kW | SAJ
8062565725 | JAIME PEREIRA | Aprovado | Aprovado | 1x5 W | SAJ | 2026-02-18
8062565902 | SONIA KRUGER | Aprovado | Aprovado | 1x15 kW | SAJ
8062565978 | JOAOZINHO MIRANDA | Reprovado |  | 2x5 kW | SAJ
8062866234 | DENILSON PEREIRA | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-02-18
8062866352 | VALMIR ADOLFO FLORIANO | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-03-03
8062881987 | ELAINE MULLER | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-02-18
8062882079 | VANDERLEI KUBICHEN | Aprovado |  | 1x5 kW | SAJ
8063480083 | EDEMAR JOSE DA SILVA | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-02-18
8063480640 | ELIZEU NALEVAIA | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-03-24
8064782612 | VALMOR DA SILVA | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-02-25
8064420876 | ANAIR PRIN KUHNEN | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-02-18
8064385288 | VIVIAN BAER | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-02-19
8063630412 | MARLENE ARANTE | Aprovado | Aprovado | 1x5 W | SAJ | 2026-02-24
8065146245 | DEUSI LEILA CAPISTRANO | Aprovado |  | 1x5 kW | SAJ
8058575114 | ROSELI LEITE | Obra |  | 2x10 kW | SAJ | 2025-12-15
8066986371 | MANOEL CACHOEIRA | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-03-26
8066608888 | JAIR DE SOUZA | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-03-31
8066609289 | MARIO MARCELINO | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-04-10
8066577379 | NERI FANTON | Aprovado | Aprovado | 2x6 kW | SAJ | 2026-03-14
8063622970 | EVANDRO MAYER | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-04-23
8063622973 | SILVANO PENZ | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-02-26
8063622977 | MARCO AURELIO BONETTI | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-02-26
8063622991 | MARCOS KNIESS
8065123058 | VANUSA SARMENTO CARDOZO LEAL | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-10
8065123410 | NILTO ODELLI | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-02-26
8065123753 | FLORIANO MALCZEVSKI | Em Analise |  | 1x3 kW | SAJ
8035375831 | LEOMAR ROQUE GOTTSCHALK | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-03-02
8067627774 | CLAUDIOMIR LEMKE | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-03-14
8067214396 | MARCOS KNIESS | Em Analise |  | 1x15 W | SAJ
8067213750 | JOAO BATISTA BECKER BERTO | Aprovado | Aprovado | 2x7,5 kW | SAJ | 2026-03-23
8067213220 | ROGERIO ADRIANO | Aprovado |  | 1x5 kW | SAJ
8067681426 | LINDOMAR DOS SANTOS | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-05-11
8067627213 | VALDECIR BECKER | Obra | 2026-04-17 | 2x5 kW | SAJ
8067719820 | CELSO SOUZA DOS SANTOS | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-03-14
8067333002 | ANTONIO DA SILVA | Aprovado | Reprovado | 1x5 kW | SAJ | 2026-04-02
8067285527 | SILVIO RODRIGO KLOSS | Aprovado | Aprovado | 1x3 kW | Growatt | 2026-03-27
8067998699 | LUIZ TOMELIN | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-04-22
8068628364 | JOSIMAR GRAUPNER | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-10
8068627881 | PAULA EMILIENA SILVEIRA | Aprovado |  | 1x6 kW | SAJ
8068909581 | DIEGO HUMENIUK | Aprovado AR | Em Analise | 2x6 kW | SAJ
8068938751 | LEONIR CATARINA CHIROLLI | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-22
8068940361 | MARIO VANDERLINDE | Aprovado |  | 1x3 kW | SAJ
8068940379 | EVALDINO SCHMITZ | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-04-22
8064690134 | JOAO GABRIEL KUCHINIR | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-06-04
8064690531 | AMILTON POPOVICZ | Aprovado |  | 1x5 kW | SAJ
8069664107 | Valdelino Warmeling abrir protocolo c/ gerador
8069663787 | jonatan felicio adriano
8068518852 | JOAO VITOR VITORIA | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-04-27
8068539251 | VALMIR MOURA VIEIRA | Verificar |  | 2x5 kW | SAJ
8068539793 | VOLNEI KOCH | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-04-22
8068626282 | LUCIANE GREIM | Aprovado | Em Analise | 2x5 kW | SAJ
8065347615 | SIRINEU SIMOES BUENO | Aprovado | Em Analise | 2x5 kW | SAJ | 2026-04-27
8065347267 | GILBERTO INACIO | ver protocolo pra trocar bifasico
8069947377 | VALDEMAR ABREU | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-03-31
8069492009 | JOSE DA ROSA | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-02
8069492304 | FAROESTE CLUBE DE CACA E TIRO | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-05-11
8069702579 | JESSICA SENEM | Aprovado | alterar | 1x7,5 kW | SAJ
8069464155 | VOLNEI ROGERIO | Reprovado |  | 1x15 kW | SAJ
8069464653 | JAIR PREIS | Aprovado |  | 2x6 kW | SAJ
8069506865 | CARLOS CONCEICAO FRANZ | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-05-11
8069511405 | FLAVIO FERREIRA | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-22
8069486407 | VANDERLEI VOLTOLINI | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-04-10
8067929852 | LUCAS DA SILVA CONHAQUE | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-10
8067939987 | GERCY JOAO DA SILVA | Aprovado |  | 1x6 kW | SAJ
8070291987 | LUCIR POSSAMAI MANKE | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-06-08
8070234350 | VENCELOR TESTONI | Reprovado |  | 1x15 kW | SAJ
8070781563 | JESSICA SENEM | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-22
8070780466 | JESSICA SCHWAMBACH RIBEIRO | Aprovado | Aprovado | 1x7,5 kW | SAJ
8050403852 | GIOVAN GIHOTSKI | alterar protocolo |  | 2x5 kW | SAJ
8070782312 | MAICON MOACIR GESSER | Obra | 2026-05-13 | 2x10 kW + 2x7,5 kW | SAJ
8071733829 | GIOVAN GIHOTSKI | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-04-22
8071560866 | ERMINIO VOLTOLINI | Aprovado | Aprovado | 1x5 W | SAJ | 2026-04-13
8069696051 | MARIA DE LURDE DUTRA | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-22
8069233119 | ANA LUCIA OTTO | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-04-22
8069211845 | JORGE ALKA | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-06-05
8070572522 | PEDRO RICARDO BOING | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-04-24
8072149517 | LUCIANO BERTO | Aprovado | Aprovado | 2x6 kW | SAJ | 2026-04-24
8070234065 | ODIRLEI RODRIGUES DUFFECK | Aprovado AR | Aprovado | 2x6 kW | SAJ | 2026-05-26
8072417296 | NELSON JOSE DE BORBA | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-05-11
8072747465 | CLAUDINEIA JUSTINO | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-05-20
8070741554 | MARCULINO CIPRIANI | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-05-11
8072219805 | ANDERSON SCHLICKAMNN | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-06-08
8072119243 | ALDO JOSE ERHARDT | Aprovado | Aprovado | 1x15 kW | SAJ | quando aprovar ampliar pra 25 kW
8072233139 | MOACIR CARARA | Aprovado | Aprovado | 1x3 kW | SAJ | 2026-05-20
8071914482 | ADEMAR XAVIER | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-06-08
8072417976 | LUCAS JOSE OBEROSLER | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-05-11
8072813879 | MARIANI ZANELLA BAUMGARTNER | Cancelado |  | 1x15 kW | SAJ
8072814202 | CELSO PERDONA | Aprovado | Aprovado | 1x5 kW | SAJ | 2026-05-21
8072853637 | ADRI-MAR INDUSTRIA E COMERCIO DE MADEIRAS LTDA - ME
8070743765 | MARINO VANDERLINDE | Aprovado |  | 1x3 W | Growatt
8072359305 | IZETE PISETTA VANDERLINDE | Reprovado |  | 1x30 kW | SAJ
8067026793 | DALVINO DA SILVA | Cancelado |  | 1x6 kW | SAJ
8067026818 | ANDRE GILI | Aprovado |  | 1x15 W | SAJ
8070577387 | EVANDRO AGNALDO TICZ | Aprovado |  | 2x5 kW | SAJ
8073897487 | GUSTAVO HENRIQUE DE AVIZ DA SILVA | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-05-20
8073898215 | VALDEMAR ABREU | Aprovado | Aprovado | 2x5 kW | SAJ | 2026-05-20
8074948284 | MARLISE VON BOEMEL ZWANG | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-05-25
8073357152 | MARIA LOURDES FUSINATO | Aprovado | Aprovado | 1x6 kW | SAJ | 2026-05-25
8073736149 | PAULA EMILIENA SILVEIRA | Aprovado | Em Analise | 1x6 kW | SAJ
beletti
8073398709 | VALMOR BELETTI | Aprovado |  | 1x5 kW | SAJ
8073399555 | JUCELIA TORQUATO ESTACIO | Aprovado | Aprovado | 1x3 kW | Growatt | 2026-05-20
8073784307 | FRANCISCO ASSIS NICOLODELLI | Aprovado | Em Analise | 1x6 kW | SAJ
8073870779 | EDINELSON AFONSO CORREA | Aprovado |  | 2x6 kW | SAJ
8074386445 | VALMOR MOSER
8075220218 | MARIANI ZANELLA BAUMGARTNER | Reprovado |  | 1x15 kW | SAJ
8054198725 | LUIZ MARCIANO | Aprovado | Aprovado | 1x15 kW | SAJ
8073182347 | RAFAEL SCHMITZ | Aprovado | Aprovado | 1x3 W | SAJ | 2026-06-08
8075397984 | HELIO SZEREMETA | OBRA |  | 1x6 kW | SAJ
8075507342 | ANTONIO GONZAGA JORGE | Aprovado |  | 2x6 kW | SAJ
8075464594 | BRUNO REIMER | Aprovado |  | 2x5 kW | SAJ
8076034064 | GILBERTO INACIO | Aprovado |  | 2x6 kW | SAJ
8076036211 | ANGELA SPIESS |  |  | 1x15 kW | SAJ
8077377580 | FELIPE FELIZARI | Em Analise |  | 1x15 W | SAJ
8076189679 | JAIME GERMANO PETRY | Em Analise |  | 1x6 kW | SAJ
8076189717 | JULIANO HAAG
8076260779 | MARIANI ZANELLA BAUMGARTNER | Aprovado | Aprovado | 1x15 kW | SAJ | 2026-06-08
8076298269 | DJONATAN FORTUNATO | Em Analise |  | 1x6 kW | SAJ
8076298033 | SERGIO LOCKS | Aprovado |  | 1x5 W | SAJ
8076291481 | MARIO FARIAS | Em Analise |  | 2x6 kW | SAJ
8076291122 | ELTON IGNACZUK
8076953214 | WALTER PREIS | Em Analise |  | 1x5 kW | SAJ
8076958269 | MAILON KROCHMALNY | Em Analise |  | 2x6 kW | SAJ
8076958509 | JONAS RENATO SENS
8077892435 | JOSEANE CRISTINA TOBIAS
8077892220 | SILVANIO RAIMUNDO
8077536205 | JUAREZ SCHOTTEN
8077370095 | VOLNEI ROGERIO
8076699602 | ADELMAR ARENDARTCHUK
8077371709 | VENCELOR TESTONI
8077374578 | ANGELA SPIESS |  |  | 1x15 kW | SAJ

## Plan2
|  | Projeto | Vistoria
| Adriana Loterio | ok | ok
| Tarcisio Cipriani | ok | ok
| Maria Padilha Neu | ok | ok
| Claudinei Possamai | ok | ok
| Anair Khunen | ok | ok
| Jair Mateucci | ok | ok
| Sonia | ok | ok
| Jaime Pereira | ok | ok
| Elaine Muller | ok | ok
| Edemar Jose da Silva | ok | ok
| Milton Amarante | ok | ok
| DENILSON PEREIRA | ok | ok
| VIVIAN BAER | ok | ok
| SOLANGE ANTUNES DUARTE FANTON | ok | obra
| jose carlso nuss | ok | ok
| valdear abreu | ok | ok
| jonas angelo bona | ok | ok
| vaderlei tamanini | ok | ok
| luiz marciano | ok | ok
| valmir adolfo floriano | ok | ok
Ampliação | Luiz henrique Cechelero
Ampliação | ademar eli
Ampliação | Pablo Vendrami
| cleide salete arcari gott | ok | ok
| leandro candido | ok | ok
| Valmor da Silva | ok | ok
| Luiz augusto paker Bertoli | ok | ok
| Silvano Penz | ok | ok
| Marcos Aurelio Bonetti | ok | ok
| Nilto Odeli | ok | ok
Floriano Malc
| Claudiomir Lemke | ok | ok
| Celso Souza dos Santos | ok | ok
| Elizeu Nalevaia | ok | ok
| Clarice Floriane vermolen | ok | ok
| Valdemar Antonio da Silva | ok | ok
| JOAO BATISTA BECKER BERTO | ok | ok
| Neri Fanton | ok | ok
| antonio da silva | ok | ok
| manoel cachoeira | ok | ok
| joao vitor vitoria | ok | ok
| erminio voltolini | ok | ok
| gustavo enrique aviz da silva | ok | ok
| jair de souza | ok | ok
| silvio kloss | ok | ok
| venderei voltolini | ok | ok
| isaltion chiquelero | ok | ok
| marcio marcelino | ok | ok
| Giovan Gihotski | ok | ok
| Joao Grabriel Kucnir | ok | ok
| Valdelino Warmeling | Fazer a ampliação material escritorio
| Vanusa Sarmento | ok | ok
| josimar graupner | ok | ok
| Lucas da silva CONhaque | ok | ok
| Leonir Catarina Chirolli | ok | ok
| Maria de Lurde Dutra | ok | ok
| Flavio Ferreira | ok | ok
| Evaldino Schmitz | ok | ok
| Guilherme Vendrami | abrir protocolo
| Dirceu Greim | ok | ok
| Silvio Fabichaki | ok | mandar para obra
| ana lucia oto | ok | ok
| volnei koch | ok | ok
| jose da rosa | ok | ok
| jessica senem | ok | ok
| Ivan da Silva | ampliação
| Larcio Tomelin | ok | ok
| Antenor Niquelatti | ok | ok
| Luciano Berto | ok | ok
| Jose Inacio | ok | ok
| Sirineu Simoes Bueno | ok | ok
| Odirlei Rodrigues Dufferck | obra
| Evandro Mayer | ok | ok
| Nelson Jose de Borba | ok | ok
| Pedro Ricardo Boing | ok | ok
| Claudineia Justino | ok | ok
| Marculino Cipriani | ok | ok
| Diego Humeniuk | ok | Repro
| Carlos Conceicao franz | ok | ok
| Paulo Emiliena Silveira | ok | ok
| Lindomar dos Santos | ok | ok
| Marcelo Greim | ok | ok
| Lucir Possamai | ok
| Moacir Carara | ok | ok
| Jorge Alka | ok | ok
| Jessica Sawalback Ribeiro | ok | ok
| Faroeste | ok | ok
| Luciane Grein | ok | ok
| Maria zAnela Baungartner | ok
| Lucas Obesrosler | ok | ok
| Jucelia Torquato | ok | ok
| Maria Lourdes Fusinato | ok | ok
| Marlise vonboelmel | ok | ok
| Francisco de assis | ok
| Celso perdona | ok | ok

## Plan3
INVERSOR SAJ | PLACA 600 W | PLACA 700 W
2,25 kW | 3 | 3
3 kW | 9 | 8
5 kW | 16 | 14
6 kW | 18 | 17
7,5 kW | 23 | 19
8 kW | 25 | 22
10 kW | 27 | 27
15 kW | 48 | 40
20 kW | 66 | 56
25 kW | 76 | 68
36 kW | 114 | 102
50 kW | 152 | 136
75 kW | 228 | 204

## Plan4
8070741554 | MARCULINO CIPRIANI
8070743765 | MARINO VANDERLINDE
8070780466 | JESSICA SCHWAMBACH RIBEIRO
8070781563 | JESSICA SENEM
8070782312 | MAICON MOACIR GESSER
8071560866 | ERMINIO VOLTOLINI
8071733829 | GIOVAN GIHOTSKI
8071914482 | ADEMAR XAVIER
8072119243 | ALDO JOSE ERHARDT
8072149517 | LUCIANO BERTO
8072219805 | ANDERSON SCHLICKAMNN
8072233139 | MOACIR CARARA
8072359305 | IZETE PISETTA VANDERLINDE
8072417296 | NELSON JOSE DE BORBA
8072417976 | LUCAS JOSE OBEROSLER
8015600075 | ADRIANO KOBREN
8015613865 | MICHELLY VON BOEMEL
8015961015 | EDEVALDO GROSSKLAUS
8016162745 | ELIZITO BENCZ
8020832583 | VALMIR FRANCISCO BILK
8020943430 | VEVERSON MENEGALLI
8020943994 | HILARIO VETTER
8021009205 | EVALDINO JOSE SCHROEDER
8021064450 | GABRIELA MORASTONI
8021064759 | IVONE GARCIA CIPRIANI
8021065128 | SERGIO BELETTI
8021065418 | ANTONIO SENEM
8021065645 | DACENA MATERIAIS ELETRICOS LTDA.
8021656861 | JUAREZ DE SOUZA
8026928476 | AROLDO DE FREIN
8035996816 | IVO MENEGHELLI
8036001034 | DARIO PINZAGHER
8036003457 | MICHAEL VOGENIAK BILIK
8036309394 | OSNI MUCHENSKI
8036310112 | REINALDO KOPPES
8036310602 | TIAGO NUNRBERG
8036523931 | PAULO VIEIRA
8036578241 | CLAUDENIR SENSI EPP
8036579808 | MARCELO DA MAIA
8036696716 | ALBERTO PREIS
8037538806 | HELITON PAULO TIBES DA SILVA
8037765839 | IRIA LUZIA STEFFEN
8037765949 | NELSO ODORIZZI
8037766949 | JOSE LUIECKMANN
8037766966 | TEODOSIO BILESKI
8037870910 | JANUARIO SCHMIDT
8038645141 | MAICON MOACIR GESSER
8038755357 | DITER MICHEL
8038756935 | CLEITON ALEXANDRE TOSE
8038757166 | JADIEL OSVALDO ERN
8038757572 | CLAUDINEI RODRIGUES
8038761474 | JUSCELI DA SILVA SARDO
8038760930 | VIVIANE BLASIUS
8038984384 | NELSO FRANCISCONI
8038985181 | ADAIR ALVES
8039099880 | FLORENTINO ZANCANARO
8039099885 | CIDNEI BLASIUS
8039099908 | VIVALDO KOPPES
8039099945 | POSTO ALTO SANTA TEREZINHA
8039099959 | GILBERTO TENFEN
8039328229 | ARLEI VENDRAMI
8039328504 | VANIO LUIZ MOSER
8039512114 | CELSO HELLMANN
8039513227 | ALEXANDRE CHIKOSKI
8039944598 | ELCIO HOEPERS
8039946515 | LIRIO NASS
8040200327 | JAMES DE OLIVEIRA
8040205168 | VILSON ALBRECHT
8040376050 | PAULO CÃ‰SAR TORQUATO
8040377587 | JAIR RIBEIRO
8041008768 | JOCENEI HELLMANN
8041065859 | PERGENTINO MANARIN
8041078845 | JANDIRA DE ANDRADE
8041079052 | ROBERTO RIVELINO MATIAS
8041846457 | ELENO CESAR WARMELING
8042345194 | JARDEL BONETTI
8042718869 | DEONISIA KORENIVSKI
8045726017 | LUIZ PATEL
8045726432 | ROLF DAHLKE
8045872180 | ALVARO LUIS MARCOS
8045977571 | RENATO BECKER
8046436061 | TULIO MARIO MONDINI
8046480094 | RENATO SCHALDACH
8046506751 | ADENIR CIPRIANI
8046507469 | JOAO SILMAR MARTINS
8046809428 | GABRIEL HELLMANN
8047058205 | SANDRO SOARES
8047700402 | LUCIA SEMANN
8047700799 | CLEYTON JOSE BARBETTA
8047709836 | AGNES ROPKE
8047757724 | RALF STALOCH
8047843907 | MARCELO FERNANDES
8047844231 | EMANOELE FERNANDES
8047904617 | AURORA CARTURANO
8048122287 | ROSELI KOPP DE OLIVEIRA BRANCO
8048376758 | ARLEI VENDRAMI
8048377244 | OSMAR SCHMITZ
8048378017 | ADRI-MAR INDUSTRIA E COMERCIO DE MADEIRAS LTDA - ME
8048404709 | AGOSTINHO SCHELL
8048475657 | ALBERTO PREIS
8048477713 | SANDRO SCHLICKMANN
8048655431 | ADENICIO JOSE DE SOUZA
8048681239 | DOUGLAS HILLESHEIM
8048707235 | MARCIO LANZNASTER
8048918329 | EDEVALDO GROSSKLAUS
8048918959 | AIRSON MARTINS
8048919825 | EVALDO PETROSKI
8049268498 | NELI PEREIRA
8049288637 | SALESIO HOEPERS
8049288826 | JUSSARA VALENCIO ROHLING
8049289184 | LAENIO WESSLER
8050011389 | JOSE CARLOS NUSS
8050305928 | ERMINIO VOLTOLINI
8050526612 | WIT FARMA FARMACIA
8050527031 | DANILO BOING
8050997847 | IRIS MONDINI
8050997877 | MARCEL MENEGHELLI
8050997904 | KEDMA MAHYARA DE OLIVEIRA
8050998177 | JONAS DOS SANTOS
8051033969 | JAIR RODRIGUES
8051034378 | ISONE DA ROSA
8051285753 | ISAILTON CHIQUELEIRO
8051441299 | VITORINO KLAUMANN
8051663676 | OSMAR INACIO
8051840591 | TIAGO COELHO
8052077176 | ADELINO STEFFEN
8052114396 | CIDNEI BLASIUS
8052148564 | LOURIVALD LAUE
8052149936 | MIRIAN PAIM DE JESUS
8052576162 | PAULO SERGIO LUNELLI
8052930447 | ANDERSON KORMANN
8053305246 | OSMAR LATAUCZESKI
8053706924 | JONAS ANGELO BONA
8054023518 | AMARILDO HASKEL
8054172185 | JOSE DA SILVA SOBRINHO
8054175945 | INEZ BORGONHO FRONZA
8054198725 | LUIZ MARCIANO
8054198883 | EDUARDO DA SILVA
8054388660 | TEREZITA PINTO DE FAVERI
8054396581 | MARCELO HAVERROTH
8054412730 | GUSTAVO HENRIQUE DE AVIZ DA SILVA
8054612536 | DARIO KRAMBECK
8054644939 | GILBERTO KURTH
8055020061 | VANDERLEI TAMANINI
8055327578 | OSMAR DA SILVA
8055369551 | JOAO SZOLOMICKI
8055407944 | ISRAELA TRAPP
8055481362 | MARLISE SOCREPPA WARMELING
8055529514 | IRMA ALEXANDRE
8056123966 | SOLANGE ANTUNES DUARTE FANTON
8056124191 | VALDEMAR ABREU
8056132000 | CHARLENE SCHMIDT TENFEN
8056566599 | PEDRO DE SOUZA
8056511542 | OSMAR LUIZ
8056514788 | OSMAR SCHMITZ
8056566648 | EMIR PAHL
8056566661 | CLARICE FLORIANI VERMOHLEN
8062565725 | JAIME PEREIRA
8062565902 | SONIA KRUGER
8062565978 | JOAOZINHO MIRANDA
8062566101 | MARIA MARIENE PADILHA NEU
8062866234 | DENILSON PEREIRA
8062866352 | VALMIR ADOLFO FLORIANO
8062881987 | ELAINE MULLER
8062882079 | VANDERLEI KUBICHEN
8063480640 | ELIZEU NALEVAIA
8063480083 | EDEMAR JOSE DA SILVA
8063622970 | EVANDRO MAYER
8063622973 | SILVANO PENZ
8063622977 | MARCO AURELIO BONETTI
8063622991 | MARCOS KNIESS
8063630412 | MARLENE ARANTE
8063634168 | CLAUDINEI JOSE POSSAMAI
8063968964 | SILVIO FABICHAKI
8063969073 | SALETE APARECIDA DALMARCO
8063969174 | VALDEMAR ANTONIO DA SILVA
8063969350 | DIRCEU GREIM
8063969677 | MARCELO GREIM
8064385288 | VIVIAN BAER
8064420876 | ANAIR PRIN KUHNEN
8064690134 | JOAO GABRIEL KUCHINIR
8064690531 | AMILTON POPOVICZ
8064782612 | VALMOR DA SILVA
8065123058 | VANUSA SARMENTO CARDOZO LEAL
8065123410 | NILTO ODELLI
8065123753 | FLORIANO MALCZEVSKI
8065146245 | DEUSI LEILA CAPISTRANO
8065347267 | GILBERTO INACIO
8065347615 | SIRINEU SIMOES BUENO
8066577379 | NERI FANTON
8066608888 | JAIR DE SOUZA
8066609289 | MARIO MARCELINO
8066986371 | MANOEL CACHOEIRA
8067026793 | DALVINO DA SILVA
8067026818 | ANDRE GILI
8067213220 | ROGERIO ADRIANO
8067213750 | JOAO BATISTA BECKER BERTO
8067214396 | MARCOS KNIESS
8067285527 | SILVIO RODRIGO KLOSS
8067333002 | ANTONIO DA SILVA
8067627213 | VALDECIR BECKER
8067627774 | CLAUDIOMIR LEMKE
8067681426 | LINDOMAR DOS SANTOS
8067719820 | CELSO SOUZA DOS SANTOS
8067929852 | LUCAS DA SILVA CONHAQUE
8067939987 | GERCY JOAO DA SILVA
8067998699 | LUIZ TOMELIN
8068518852 | JOAO VITOR VITORIA
8068539251 | VALMIR MOURA VIEIRA
8068539793 | VOLNEI KOCH
8068626282 | LUCIANE GREIM
8068627881 | PAULA EMILIENA SILVEIRA
8068628364 | JOSIMAR GRAUPNER
8068909581 | DIEGO HUMENIUK
8068938751 | LEONIR CATARINA CHIROLLI
8068940379 | EVALDINO SCHMITZ
8068940361 | MARIO VANDERLINDE
8069211845 | JORGE ALKA
8069233119 | ANA LUCIA OTTO
8069464155 | VOLNEI ROGERIO
8069464653 | JAIR PREIS
8069486407 | VANDERLEI VOLTOLINI
8069492009 | JOSE DA ROSA
8069492304 | FAROESTE CLUBE DE CACA E TIRO
8069506865 | CARLOS CONCEICAO FRANZ
8069511405 | FLAVIO FERREIRA
8069662218 | BRUNA CRISTINA RODRIGUES MOSER
8069663787 | JONATAN FELICIO ADRIANO
8069664107 | VALDELINO WARMELING
8069696051 | MARIA DE LURDE DUTRA
8069702579 | JESSICA SENEM
8069947377 | VALDEMAR ABREU
8070234065 | ODIRLEI RODRIGUES DUFFECK
8070234350 | VENCELOR TESTONI
8070291987 | LUCIR POSSAMAI MANKE
8070572522 | PEDRO RICARDO BOING
8070577387 | EVANDRO AGNALDO TICZ
8063622970 | EVANDRO MAYER
8063622973 | SILVANO PENZ
8063622977 | MARCO AURELIO BONETTI
8063622991 | MARCOS KNIESS
8063630412 | MARLENE ARANTE
8063634168 | CLAUDINEI JOSE POSSAMAI
8063968964 | SILVIO FABICHAKI
8063969073 | SALETE APARECIDA DALMARCO
8063969174 | VALDEMAR ANTONIO DA SILVA
8063969350 | DIRCEU GREIM
8063969677 | MARCELO GREIM
8067719820 | CELSO SOUZA DOS SANTOS
8072813879 | MARIANI ZANELLA BAUMGARTNER
8072814202 | CELSO PERDONA
8072853637 | ADRI-MAR INDUSTRIA E COMERCIO DE MADEIRAS LTDA - ME
8073357152 | MARIA LOURDES FUSINATO
8073398709 | VALMOR BELETTI
8073399555 | JUCELIA TORQUATO ESTACIO
8073784307 | FRANCISCO ASSIS NICOLODELLI
8073870779 | EDINELSON AFONSO CORREA
8073897487 | GUSTAVO HENRIQUE DE AVIZ DA SILVA
8073898215 | VALDEMAR ABREU
8074386445 | VALMOR MOSER
8075220218 | MARIANI ZANELLA BAUMGARTNER